## Sprint Summary
Averages (3 Sprint Rolling Avg)
User Stories | 14
Story Points | 41
Story point adjusted | 48
Engineers in team
|  | Engineers | 4
Standard sprint length
|  |  |  | Days | 10
Sprint Summaries 2019
[7 empty] | User Stories |  |  |  | Story Points |  |  |  |  | Engineers | Days | Days Leave
[6 empty] | Sprint | Planned | Actual | Var | Var % | Planned | Actual | Adj | Var | Var % | Actual | Actual | Planned | Actual | Comments (number in brackets is days off)
[6 empty] | 24 | 39 | 47 |  |  | 181 | 181
[6 empty] | 25 | 25 | 40 |  |  | 180 | 191
[6 empty] | 1 | 19 | 21 | 2 | 10.53% | 34 | 35 | 35 | 1 | 2.941% | 4 | 10 | 0 | 0
[6 empty] | 2 | 12 | 15 | 3 | 25% | 55 | 56 | 56 | 1 | 1.818% | 4 | 10 | 1 | 2
[6 empty] | 3 | 14 | 13 | -1 | -7.143% | 51 | 52 | 52 | 1 | 1.961% | 4 | 10 | 10 | 10
[6 empty] | 4 | 13 | 15 | 2 | 15.38% | 22 | 21 | 42 | -1 | -4.545% | 4 | 5 | 2 | 2
[6 empty] | 5 | 14 | 14 | 0 | 0% | 47 | 50 | 50 | 3 | 6.383% | 4 | 10 | 3 | 3
[6 empty] | 6 |  |  | 0 | 0% |  |  |  | 0 | 0%
[6 empty] | 7 |  |  | 0 | 0% |  |  |  | 0 | 0%

## Sprint Template
Sprint x
| Days | Done | Planned Left | Board | Actual Left | Ideal | Comments
| 0 |  | 37 |  | 37 | 37
Mon | 1 |  | 33.3 |  | 33.3 | 33.3
Tues | 2 |  | 29.6 |  | 29.6 | 29.6
Wed | 3 |  | 25.9 |  | 25.9 | 25.9
Thu | 4 |  | 22.2 |  | 22.2 | 22.2
Fri | 5 |  | 18.5 |  | 18.5 | 18.5
Mon | 6 |  | 14.8 |  | 14.8 | 14.8
Tues | 7 |  | 11.1 |  | 11.1 | 11.1
Wed | 8 |  | 7.4 |  | 7.4 | 7.4
Thu | 9 |  | 3.7 |  | 0 | 3.7
Fri | 10 |  | 0 |  | 0 | 0
| Total: | 0
Planning
[9 empty] | Planned | Actual | Comments
[8 empty] | Start Date | 2020-05-11
[8 empty] | End Date | 2020-05-22
[8 empty] | Number of Days | 10
[8 empty] | Number of Story Points | 37
[8 empty] | Number of Stories | 8
[8 empty] | Ideal Velocity (Points) | 3.7
[8 empty] | Ideal Velocity (Stories) | 0.8
[8 empty] | Developers | 4
[8 empty] | Total leave days | 0
Formulas:
Planned = WORKDAY([Planned, row above],9)

## Completed Sprint Example
Sprint x
| Days | Done | Planned Left | Board | Actual Left | Ideal | Comments
| 0 |  | 47 |  | 47 | 47
Mon | 1 | 10 | 37 | 37 | 37 | 42.3
Tues | 2 | 10 | 27 | 27 | 27 | 37.6
Wed | 3 | 3 | 24 | 25 | 25 | 32.9
Thu | 4 | 8 | 16 | 17 | 17 | 28.2
Fri | 5 | 1 | 15 | 16 | 16 | 23.5
Mon | 6 | 4 | 11 | 11 | 11 | 18.8
Tues | 7 | 4 | 7 | 9 | 9 | 14.1
Wed | 8 | 4 | 3 | 4 | 4 | 9.4
Thu | 9 | 4 | -1 | 1 | 0 | 4.7
Fri | 10 | 0 | -1 | 0 | 0 | 0
| Total: | 48
Planning
[9 empty] | Planned | Actual | Comments
[8 empty] | Start Date | 2020-04-27
[8 empty] | End Date | 2020-05-08
[8 empty] | Number of Days | 10
[8 empty] | Number of Story Points | 47 | 48
[8 empty] | Number of Stories | 14 | 20
[8 empty] | Ideal Velocity (Points) | 4.7
[8 empty] | Ideal Velocity (Stories) | 1.4
[8 empty] | Developers | 4 | 4 | Team at full strength
[8 empty] | Total leave days | 1 | 1 | Sebastian, one day leave.
Formulas:
Planned = WORKDAY([Planned, row above],9)